NSS VIIT (A)

# Implementation Plan

Phases, workstreams, testing, risk management and launch readiness (Integrated with MY Bharat)

DESIGN PRINCIPLE  Extraordinary visual craft, purposeful motion, institutional trust and accessible interaction.

| Document control | Value |
| --- | --- |
| ID | DOC-06 |
| Version | 2.0 — integrated baseline (with MY Bharat expansion) |
| Project | NSS VIIT (A) — complete website and digital platform |
| Status | Requirements baseline; not an implementation or testing claim |
| Approval | Review by both primary NSS administrators and college-authorized authority where applicable |

# 1. Delivery approach

Implement in controlled phases from a clean project. Confirm institutional and policy questions before locking providers or enabling registration. Incorporate MY Bharat natively into public pages, multi-track registration, event management and attendance auditing. Launch only after critical workflows, security, accessibility, recovery and joint approvals pass.

# 2. Delivery phases

| Phase | Work Description | Exit Criteria |
| --- | --- | --- |
| 0. Governance | Confirm domain, eligibility fields, joint-event hour formula, certificate rules, MY Bharat cell intake rules, privacy. | Open questions and responsible authorities documented. |
| 1. Architecture & Design | Confirm React + TS + Tailwind tokens; define RBAC, environments, routes (/my-bharat), and incorporate Stitch UI. | TRD, Stitch design system and token baseline reviewed. |
| 2. Public Website | Build Home, About NSS, MY Bharat (dedicated page), Events, Calendar, Gallery, Team (28 members), Volunteer Info, Resources, Contact. | Responsive public pages; only approved content; registration closed banner visible. |
| 3. Identity & Permissions | Authentication, role model (including MY Bharat Coordinator & PO Reviewer), admin MFA, session revocation. | Positive and negative authorization tests pass. |
| 4. Multi-Track Registration | Unified registration flow (NSS/Bharat/Both), admin review queues, account statuses, alumni history. | Registration remains disabled by default; lifecycle tests pass. |
| 5. Events, Attendance & Hours | Event proposals (NSS/Bharat/Joint), capacity rules, manual attendance, audit log, distinct hour ledgers (no double-counting). | No overbooking; audited corrections; zero double-counting verified. |
| 6. Collaboration Workspaces | Core Team tasks, restricted attachments, meeting minutes, notices, support tickets, confidential reports. | Permissions and notification delivery tests pass. |
| 7. Media, Reports & Certs | Media review workflow, album curation, PDF exports, annual reports, certificate approval workflows. | No private leakage; exports and issuance tested. |
| 8. Hardening & Quality | Security audit, WCAG 2.2 AA accessibility, performance profiling, backup restore test. | Critical findings resolved; restore drill evidence recorded. |
| 9. Private Preview | Load approved content; test with primary NSS admins, MY Bharat coordinators, and college authority on mobile/desktop. | Both admins and college reviewer approve or record blockers. |
| 10. Launch & Handover | Joint approval, production deployment, monitoring and runbook transfer. | Two maintainers trained; rollback available; registration opens only by separate authorized decision. |

# 3. Workstreams

Product & Content: approved copy, official resources, event data, bios (24 NSS, 4 Bharat), media consent and reports.

Design: tokens, responsive layouts, motion system, Stitch UI incorporation, accessibility and dashboard IA.

Frontend: pages, dedicated MY Bharat landing, dashboards, forms, filters, calendar, animations and UI states.

Backend & Data: schema, RLS policies, multi-track authorization, workflow rules, audit and reporting.

Operations: domain, environments, secrets, monitoring, backups, restore and incident runbooks.

QA: unit, integration, e2e, permissions, accessibility, device and performance testing.

# 4. Testing strategy

Unit tests: service-hour calculation (verifying zero double-counting for joint events), multi-track filtering, state transitions and permissions.

Integration tests: multi-track registration, dual approval queues, attendance corrections, notifications, media review and certificates.

End-to-end tests: user journeys across public site (including /my-bharat) and all private workspaces.

Negative authorization tests: MY Bharat coordinator attempting to edit NSS unit records; volunteer attempting peer record access; revoked sessions.

Concurrency tests: event registration capacity limits under load.

Accessibility & Performance: WCAG 2.2 AA automated/manual checks; mobile responsiveness on mid-range devices; reduced motion tests.

Email failure & recovery: transactional retry tests; never assume delivery without confirmation.

# 5. UI animation checklist

Use reusable motion tokens/variants; avoid one-off effects everywhere.

Hero carousel: pause/play, previous/next, indicators, keyboard control and reduced-motion fallback.

Navigation drawer: focus management, Escape key listener, backdrop close and body scroll lock.

Prefer transform and opacity; avoid layout recalculations and heavy scroll listeners.

Test on mid-range mobile devices; critical actions must remain immediate without animation delays.

# 6. Launch checklist

Official domain approved; ownership and handover documented.

Primary administrators use MFA; recovery procedures verified.

Role matrix and revoked-session behavior tested across all roles.

All published content, photos, contacts and resources approved; zero fabricated content.

Volunteer registration stays closed until separately authorized.

Roster verification: 28 Core Team members confirmed (24 NSS, 4 MY Bharat) prior to team page release.

Service-hour calculation rules and joint-event crediting formula confirmed by Programme Officer.

Backup and restore test succeeds; actual provider limits verified.

Both primary admins and college authority grant explicit written launch approval.

Two technical maintainers trained and runbooks handed over.

# 7. Risks and mitigations

| Risk | Mitigation Strategy |
| --- | --- |
| Double-counting joint event hours | Strictly separate hour ledgers (nss_hours vs my_bharat_hours); enforce calculation rules in server-side workflows. |
| Brittle team count constraint | Use administrative pre-publish validation checks instead of hard database constraints to prevent editing deadlocks. |
| Unverified institutional policy | Preserve open questions as 'Pending Institutional Confirmation'; obtain written sign-off before configuring thresholds. |
| Accidental registration opening | Enforce feature flag defaulting to false; show persistent closed banner in UI. |
| Excessive admin privilege | Strict least-privilege RBAC; separate Website Admin, Operations Admin, and MY Bharat Coordinator roles. |

# 8. Handover package

Source repository and release workflow.

Provider/account inventory, environment setup and secret rotation instructions.

Database restore runbooks and incident response procedures.

Data dictionary, permission matrix, test evidence and signed launch approvals.

# 9. Completion definition

Launch readiness requires complete implementation of approved NSS and MY Bharat features, passing critical security and accessibility tests, verified private-data boundaries, demonstrated backup restoration, approved authentic content, and recorded joint launch approval. Volunteer registration opens exclusively by separate authorized decision.